## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sudheer Bellamkonda | 2026-07-19 | Metadata key mismatch (resolution vs solution) | Sprint 1 | Sudheer Bellamkonda | Functional | Updated metadata mapping in vectordb.py | 2026-07-19 | Closed | Fixed
2 | Sudheer Bellamkonda | 2026-07-19 | Syntax error in main.py | Sprint 1 | Sudheer Bellamkonda | Code | Corrected syntax and verified API | 2026-07-19 | Closed | Verified
3 | Sudheer Bellamkonda | 2026-07-19 | README.md created with wrong extension | Sprint 1 | Sudheer Bellamkonda | Documentation | Renamed to README.md | 2026-07-19 | Closed | Fixed
4 | Sudheer Bellamkonda | 2026-07-19 | requirements.txt saved with incorrect extension | Sprint 1 | Sudheer Bellamkonda | Documentation | Renamed to requirements.txt | 2026-07-19 | Closed | Fixed
5 | Sudheer Bellamkonda | 2026-07-19 | GitHub remote not configured | Sprint 1 | Sudheer Bellamkonda | Configuration | Added remote and pushed repository | 2026-07-19 | Closed | GitHub updated

## Sheet2
Category | Count
Logical | 2
User Interface | 0
Maintainability | 1
Standards | 2
Others | 0